PROGRESS REPORT for EPC-19-060

March 2022

Recipient Project Manager: Sarah Kurtz

Commission Agreement Manager: Jeffrey Sunquist

What we planned to accomplish this period

- We will complete final version of the Deliverable for Task 4.2

- We will continue to meet with stakeholders and community representatives to gather inputs and request feedback

- We will extend the implementation of the variable time steps to the PSP scenario.

- We will continue the SWITCH studies #1, #3 and #4 and will begin reporting more consistently on their status.

- We will prepare the deliverable for Task 3.4.

What we actually accomplished this period

Note: the numbering of items 1-5 above is reported in the heading style with italics. Our efforts for item #3 are included with its own numbering starting on page 2 and going through page 7.

1. Complete Draft Grid Scenario for Task 4.2

The Revised Grid Scenario Summary was submitted. It is included in this package for reference.

2. Stakeholder and collaborator meetings: During the month of March, we met with:

- Attended the California Energy Storage Alliance’s Annual Market Development Forum in Berkeley – this is an invitation only meeting and offered an opportunity to meet a number of new people who are working on storage

- Roderick Go at E3

- Julia Prochnik of the Long-Duration Energy Storage Association of California.

- Sarah Kurtz gave a presentation for CEC project EPC-19-051 Hybrid-Modular Storage Solution (HMSS) Rapid Integration & Commercialization Unit (RICU) TAC meeting

- Andrew Hartshorn of PolyJoule

- Patricia Hidalgo-Gonzalez gave a second open presentation on some results obtained using SWITCH

- Sarah Kurtz gave a presentation for group of utility representatives for a Darcy-hosted meeting entitled “De-risking LDES technologies with Indian Energy”

3. Implement variable time steps into RESOLVE code

We had targeted completing the implementation of the variable time step calculation to the PSP this month, but we ran into some snags we had not expected.   The implementation is complex for the full-size model, but we are fortunate that E3 identified this as a problem and created “Scenario tags”. The use of the Scenario tags greatly simplifies implementation of the variable time steps method, but changing direction cost us a little time during the implementation process.

To share a subset of the progress we have made, we include here the step-by-step description of the process we are implementing in the file handling.

Steps for implementing the two-step process using critical (variable) time steps.

Goal: The goal of this modification is to enable capacity expansion planning in a two-step process that is a) similar to how the world works, and b) more importantly, we anticipate that it will provide a more computationally efficient way to obtain accurate answers, especially when storage is being used to store energy for more than 24 hours.

The selection of the critical time steps is described in a different document. The output of that process is the rep_periods.csv file with the first time point being hour 0:00 for January 1 and the last time point being 23:00 on Dec. 31.

Scenario/scan naming strategy.

Baseline: Whatever scenario we are starting with.  The details may vary depending on what scenario we start with.

CTS: critical time points will be the first pass

HD: hourly dispatch will be the second pass

Part 1. Preparation for calculating the required capacity expansion to meet resource adequacy at the “critical times” when we expect storage to be fully filled or fully emptied and when we expect that the net load (defined as the load minus the solar and wind) will be highest. Part 1 needs to modify the input files in both the temporal settings folder and the input data to align with the new time points.

1. Create Settings files

i. Duplicate settings folder within

new-modeling-toolkit/data/settings/resolve/[scenario name]  and add “_CTS” to the folder name for the new scenario

Duplicate all of the files inside of this folder except the rep_periods.csv, which will be overwritten

ii. Append to scenarios.csv file: Using [Scenario name] that is input as a parameter, append to scenarios.csv file (or create it) “CTS”

Store it at:

• new-modeling-toolkit/data/settings/resolve/[Scenario name_CTS]/scenarios.csv

File content should be (in order to prioritize CTS over B):

scenarios

B

CTS

2. Define changes needed for the data in the interim folder by inspecting/updating the components.csv file:

a) Identify components that will need to be modified

• The components.csv file can be found in new-modeling-toolkit/data/interim/systems/[scenario name]/components.csv where [scenario name] may be specified as an input parameter.

The format for the components.csv file is:

| component | instance |
| --- | --- |
| Load | zone_1 |
| Resource | Solar |
| Resource | Wind |
| Resource | Gas_CCGT |
| Resource | Gas_CT |
| Resource | Battery |
| Zone | zone_1 |

Note that the components.csv file specifies “component” and “instance”

• Each component should be handled differently as described in Table 1.

Table 1. Identification of components to be updated

| “component” | Ignore | Modify attributes.csv file for this instance and create time series file |
| --- | --- | --- |
| CandidateFuel | X |  |
| ELCCSurface | X |  |
| Load |  | X |
| Policy | X |  |
| Reserve |  | X |
| Resource | Others | If “solar” or “wind” appears in name |
| TXPath | X |  |
| Zone | X |  |

3. Modify data files for each instance in the components lists. Note: The existing code does some of this

a) Modify attributes.csv file for each instance (two modifications here):

i) If needed: add a fourth column “scenario” to each “attributes.csv” file for each instance in

new-modeling-toolkit/data/interim/[component folder]/[instance name]/attributes.csv

Where “component folder” = “loads”, “reserves”, or “resources” and “instance name” are taken from the components.csv file opened in step 2 (note that the component folder name usually has an “s” (e.g. “loads”) added to the component listed in Table 1 (e.g. “load”).)

ii) Add data to attributes.csv files processed as indicated in Table 2 using the format in Table 3.

The timestamps are entered to match the critical time steps and the values record the average or the maximum value for the time interval recorded at the beginning of the time interval (in the given example, the 1/1/07 00:00 value is calculated from entries for 00:00-07:00 and the 1/1/07 08:00 value is calculated from values from 08:00 to 15:00.), using Table 2 as the guide for the type of processing.  The critical time steps are taken from the rep_periods.csv file described in the introduction. The scenario column is defined as CTS for all of the new data.

Table 2. Guide for modification of values of attributes to reflect the critical time steps

| “component” | Attribute to update | Processing |
| --- | --- | --- |
| Load | profile | Average |
| Reserve | requirement | Maximum |
| Resource | provide_power_potential_profile | Average |

Table 3. Format of profile.csv file

| timestamp | Attribute | value | scenario |
| --- | --- | --- | --- |
| 1/1/07 00:00 | [See Table 2] | 0.0 | CTS |
| 1/1/07 08:00 | [See Table 2] | 0.145 | CTS |
| 1/1/07 16:00 | [See Table 2] | 0.723 | CTS |

4. How to handle the rep_periods.csv file in the settings folder?

Replace the rep_periods.csv file with one that includes only the critical time steps as described in the introduction.

5. Run the Scenario: This completes the preparation for the first optimization run. The run should be executed using the original scenario name (the scenarios.csv file will now override and supply the “CTS” data instead of the original where it was specified.)

Part 2. Preparation for second calculation which uses the capacity expansion plan from the first step and then applies an hourly dispatch to confirm that the load can be met at every hour of the year.  This second pass should create an _hd version for each period that was modeled (for example, 2030, 2035, 2040, 2045)

1. Create Settings files

i. Duplicate settings folder within

new-modeling-toolkit/data/settings/resolve/[scenario name]  and add “_hd” to the folder name for the new scenario

ii. Modify scenarios.csv file: Using [Scenario name] that is input as a parameter, modify the file to add a line with hd and the period, if there was more than one period.

Store it at:

• new-modeling-toolkit/data/settings/resolve/[Scenario name_hd]/scenarios.csv

File content should be something like (most important thing is that the last line is “hd” or “hd_2030” if we want to optimize the dispatch for each period separately):

scenarios

CTS

B

hd[_2030]

2. Identify the Operating capacities that were planned by the first step.

a) Find the correct output folder:

In folder new-modeling-toolkit/reports/resolve/[Scenario name_CTS]/[date/time of run]/expressions/[results file name] we can find the results.

Because the date/time format is a little awkward, it may be useful to select the most recently run results file.

Note: If the scenario has been run more than once and we want to use something other than the most recent calculation, the time of the run may need to be specified as an input parameter.  An example of the name of the folder is “2022-03-10 23-45-29”

b) Find the correct output files:

Within the “expressions” folder identified in Step 2, we will be working with two output files:

• “Operational_Capacity_in_Model _Years.csv”

• “Operational_Storage_in_Model _Years.csv”

The format of the results “Operational_Capacity_in_Model _Years.csv”  file is

| ASSETS | MODEL_YEARS | Operational_Capacity_In_Model_Year |
| --- | --- | --- |
| Solar | 2030 | 342802.19 |
| Wind | 2030 | 8000 |
| Battery | 2030 | 24431.2 |

3. Update items in resources and tx_paths folder:

a) Identify the files that need to be modified. Files can be found in these two locations:

• new-modeling-toolkit/data/interim/resources/[instance name]

Or

• new-modeling-toolkit/data/interim/tx_paths/[instance name]

Where the instance name matches the item in the ASSETS list. This will be done for every distinct item in the ASSETS list.

b) Add a line for build status in each file for each ASSET in the Operational_Capacity_in_Model_Year table:

| timestamp | attribute | value | scenario |
| --- | --- | --- | --- |
| None | can_build_new | 0 | hd |

Note: there should have already been a line that set “Can_build_new” to 0 or 1. Please leave that line untouched as we will go back to that when we aren’t running the “hd” scenario.

c) Add Operational Capacity data: Add a line in each file for each entry in the Operational_Capacity_in_Model_Year table (see Table 4 for more guidance):

| timestamp | attribute | value | scenario |
| --- | --- | --- | --- |
| 1/1/30 | planned_installed_capacity | 8000 | hd |

Note: there may already be lines for “planned_installed_capacity”. If these had “scenario” set to hd, then please overwrite them. If the scenario was not specified, please add new lines.

When constructing these lines, the values in the “Operational_Capacity_in_Model_Year should be transcribed using Table 4 as a guide

Table 4. Values to map from Operational_Capacity_in_Model _Years.csv to the revised attributes.csv files

| Column in results file | What to do | Where it ends up |
| --- | --- | --- |
| ASSETS | Identify the appropriate attributes.csv file |  |
| MODEL_YEARS | Convert year to a timestamp format using Jan. 1 of that year for the day | Enter as “timestamp” in attributes.csv file |
| Operational_Capacity_in_Model_Year | Copy value without change | Add entry to attributes.csv file, using timestamp from MODEL_YEARS, attribute “planned_installed_capacity” and value from this column |

d) Update build plan for Storage Capacity:

Note: this step will only be included if the resource (instance) is one that is storage. This step will be skipped for the majority of the attributes.cvs file updates.

The format for the “Operational_Storage_in_Model_Year” file is

| RESOURCES_WITH_STORAGE | MODEL_YEARS | Operational_Storage_In_Model_Year | scenario |
| --- | --- | --- | --- |
| Battery_CTS | 2030 | 901776.21 | hd |

The values in the “Operational_Storage_in_Model_Year should then be entered in the relevant attributes.csv file using Table 5 as a guide

Table 5. Values to map from Operational_Storage_in_Model _Years.csv to the revised attributes.csv files

| Column in results file | What to do | Where it ends up |
| --- | --- | --- |
| RESOURCES_WITH_STORAGE | Match to item in ASSETS and to the name of the folder with the attributes.csv file we are modifying |  |
| MODEL_YEARS | Convert year to a timestamp format using Jan. 1 of that year for the day | Enter as “timestamp” in attributes.csv file |
| Operational_Storage_in_Model_Year | Copy value without change | Add entry to attributes.csv file, using timestamp from MODEL_YEARS, attribute “planned_storage_capacity” and value from this column |

For both c) and d) be sure to include the “hd” entry in the scenario column.

“Adding a line” includes resaving the files in all cases.

4. Update rep_periods.csv file in the settings folder:

The actions for this are almost identical to those for step #4 in Part 1

The rep_periods.csv file should be replaced with one that has hourly data for the same year that is being used elsewhere.

Note that we have assumed that the provide_profile data were given in the original attributes file for every hour of the year. If they were only given for 37 days, then we will need to identify new data for this.

See notes for step #4 in Part 1.

5. Run the Scenario: This completes the preparation for the simulation: The _hd scenario should then be run by running the original scenario name.

4. Updates on SWITCH studies #1, #3, and #4 and previous paper updates

From our previous list of papers,

- #6 was accepted and is now in press

- #5b was submitted to joule after a quick review by the editor encouraged submission there.

Regarding the 5 SWITCH studies

Study 1:

Staadecker, M. et al, “The value of long-duration energy storage and its interaction with a zero-emissions western North-America electricity grid”

Status: This study is nearing completion and the manuscript is being developed.

Study 3:

Sanchez-Perez, P. and Serna Torre, P. et al. “Infrastructure and economic opportunities for California to leverage WECC resources to achieve 100% RE by 2045”

The objective of this study is to analyze the benefits in electricity prices and overall cost reduction from allowing imports from outside California. The analysis looks at impacts on supply and storage infrastructure and in-state required generation. Particularly focusing on the impacts related to LDES duration and operation. We perform a systematic study by analyzing capacity expansion optimal results from varying allowed imports in 2050 from 100% (no constraint on imports) and monotonically decreasing allowed imports by 10% all the way down to 0% (California independent from the rest of the WECC).

Status: Ongoing study. We expect to have a manuscript draft by May 2022. The initial findings of this study have revealed more subtleties than we expected (e.g., California might not need to rely on imports by 2050 from a least cost perspective). Thus, the team has been testing more scenarios and hypothesis to provide meaningful insights to the CEC and the energy community. We aim to understand what are the benefits (infrastructure and cost) provided by storage in a future where California might not want to depend on imports and other findings related to the value of storage and the coordination (or lack of) between California and the rest of the WECC.

Study 4:

Sanchez-Perez, P., Gonzalez, N., Srivastava, A. and Serna Torre, P. et al. “Impacts of re-designing planning and operational reserves rules on capacity expansion and operation”

The objective of this study is to understand the infrastructure impacts and storage needs of defining reserves in different ways for a zero emissions grid. Ultimately, this study will help regulators understand expected needed storage infrastructure to be able to satisfy reserves requirements as they might evolve over time (2050 reserves requirement design).

More specifically, we are analyzing how the infrastructure and operations would change depending on which technologies are eligible to provide planning reserves (thermal plants, renewables, and storage, or storage only). We have also been studying what are the impacts of modeling subregional planning reserves across the WECC. Last, we plan to study the impact of seasonal requirements for planning reserves.

Status: Ongoing study. We expect to have a manuscript draft by May 2022.

5. Prepare the deliverable for Task 3.4

This deliverable was prepared for submission in early April.

How we are doing compared to our plan

We have made great progress, but we still have a long way to go.

Significant problems or changes

Invoicing is still behind. We have now completed the invoice through September 2021 and have begun work on an invoice through December 2021. The individual who was doing our invoicing left the university. The person who took over for her had a double work load, so was not able to make fast progress, but is taking action and we hope to have an invoice submitted by the end of April.

The SWITCH part of Task 5.1 is already completed, but the RESOLVE part is behind schedule. E3 has indicated that they will be releasing the last elements of the new modeling toolkit to us in mid April. In the update on item #3 above (implementation of the 2-step process), we have made good progress, but have not yet completed and tested the software. We can turn in the deliverable for 5.1 on time, but it will be a more useful document if it is delayed. Also, once that is completed, we will be ready to schedule TAC meeting #3. We are appreciative of the CEC’s patience with our efforts.

What we expect to accomplish during the next period

- Submit the deliverable for Task 3.4

- We will continue to meet with stakeholders and community representatives to gather inputs and request feedback

- We hope to complete the extension of the implementation of the variable time steps to the PSP scenario.

- We will continue the SWITCH studies #1, #3 and #4. We anticipate that study #1 will be submitted in April and that data will be organized for #3 and #4 to begin writing in May

- We will prepare the deliverable for Task 5.1.

Status of Milestones and Products.

| Task # | Task | Deliverable | Due date | Status |
| --- | --- | --- | --- | --- |
| 1.2 | Kick-off meeting | Updated budget | 9/18/2020 | Complete |
| 1.3 | CPR Meeting #1 | CPR Meeting #1 | TBD |  |
|  | CPR Meeting #2 | CPR Meeting #2 | 1/21/22 | Complete |
| 1.4 | Final meeting | Final Meeting | 11/11/22 |  |
|  |  | Schedule for closeout | 11/18/22 |  |
|  |  | Draft and Final Written Products | 11/18/22 |  |
| 1.5 | Progress Reports & Invoices | Progress Reports | Monthly | Ongoing |
|  |  | Invoices | Monthly | Ongoing |
| 1.6 | Final Report | Draft Outline | 6/30/22 |  |
|  |  | Final Outline | TBD |  |
|  |  | Draft Report | 8/30/22 |  |
|  |  | Final Report | 10/31/22 |  |
|  |  | Written Responses to Comments on Draft Report | 9/15/22 |  |
| 1.7 | Match funds | Status letter | 9/9/20 | Revision submitted |
| 1.9 | Subcontracts | Final subcontracts | TBD | Completed |
| 1.10 | TAC | List of potential members | 9/9/20 | Completed |
|  |  | List of TAC members | TBD | Completed |
|  |  | Documentation of TAC member commitment | TBD | Completed |
| 1.11 | TAC Meetings | Draft TAC meeting schedule | 10/1/20 | Completed |
|  |  | TAC meeting 1 | 11/4/20 | Completed |
|  |  | TAC meeting 2 | 8/5/21 | Completed |
|  |  | TAC meeting 3 | 2/3/22 |  |
|  |  | TAC meeting 4 | 11/2/22 |  |
|  |  | Note, each meeting need multiple actions |  |  |
|  |  | Final TAC meeting schedule | TBD | Completed |
|  |  | Draft TAC meeting agenda | TBD | First one completed |
|  |  | Backup materials | TBD | First one completed |
|  |  | Final TAC Meeting agenda | TBD | First one completed |
|  |  | TAC meeting summaries | TBD | First one completed |
| 2.1 | Data assembly | Draft baseline description | 2/4/21 | Completed |
|  |  | Final baseline description | 2/25/21 | Completed |
| 2.2 | Confirmation of baseline data and approach | Draft modeling approach description | 2/4/21 | Completed |
|  |  | Final modeling approach description | 2/25/21 | Completed |
| 2.3 | Implementation of baseline data into models to create initial baseline scenario | Summary of baseline model results | 3/23/21 | Completed |
|  |  | CPR Report #1 | 15 days prior | Completed |
| 3.1 | Evaluate and document future energy storage technology alternatives | Draft storage Technology summary | 7/2/21 | Completed |
|  |  | Final storage technology summary | 8/12/22 |  |
| 3.2 | Define representative future energy storage technology alternatives | Draft proposed storage scenarios summary | 6/1/22 |  |
|  |  | Final | 8/12/22 |  |
| 3.3 | Evaluate and document future energy electricity generation technology alternatives | Draft electricity generation technology summary | 8/2/21 | Completed |
|  |  | Final | 8/12/22 |  |
| 3.4 | Define representative future electricity generation technology alternatives | Draft proposed electricity generation scenarios summary | 4/1/22 | Completed |
|  |  | Final | 8/12/22 |  |
| 4.1 | Multi-day model optimization | Summary of multi-day baseline model results | 9/2/21 | Completed |
|  |  | CPR #2 | Summer |  |
| 4.2 | Grid scenario selection | Draft grid scenario summary | 2/8/22 | Completed |
|  |  | Final | 3/7/22 | In progress |
| 5.1 | Preliminary Scenario Analysis | Draft preliminary analysis summary | 5/4/22 |  |
|  |  | Final | 5/16/22 |  |
| 5.2 | Final scenario analysis | Draft final analysis summary | 6/10/22 |  |
|  |  | Final | 8/12/22 |  |
| 6.1 | Initial public meetings | Opening workshop presentation materials | 11/17/20 | Completed |
|  |  | Northern CA workshop | 12/3/20 | Completed |
|  |  | Southern CA workshop | 12/3/20 | Completed |
|  |  | Opening workshop summary | 1/8/21 | Completed |
| 6.2 | Public workshop for grid scenario selection | Agenda | 11/2/21 | Completed |
|  |  | Presentation materials | 11/2/21 | Completed |
|  | Public workshop with CEC and TAC to present proposed scenarios |  | 11/16/21 | Completed |
|  |  | Workshop summary | 11/23/21 Summarize public comments: 12/17/21 | Completed |
| 6.3 | Public workshop for preliminary scenario analysis | Agenda | After 5.1 draft |  |
|  |  | Presentation materials | After 5.1 draft |  |
|  | Public Workshop with CEC and TAC to present preliminary analysis |  | After 5.1 draft |  |
|  |  | Workshop summary | After 5.1 draft |  |
| 6.4 | Public Workshop for Final Scenario Analysis | Agenda | 7/1/22 |  |
|  |  | Presentation materials | 7/1/22 |  |
|  | Public workshop with CEC and TAC to present final analysis |  | 7/15/22 |  |
|  |  | Workshop summary | 7/22/22 |  |
| 7 | Evaluation of Project Benefits | Kick-off meeting benefits questionnaire | 9/18/20 | Completed |
|  |  | Final meeting benefits questionnaire | 10/14/22 |  |
| 8 | Knowledge transfer activities | Draft initial fact sheet | 7/23/20 | Completed |
|  |  | Final initial fact sheet | 7/30/20 | Completed |
|  |  | Draft final project fact sheet | 7/21/22 |  |
|  |  | Final project fact sheet | 7/28/22 |  |
|  |  | Draft knowledge transfer plan | 12/31/20 | Completed |
|  |  | Final knowledge transfer plan | 2/26/21 | Completed |
|  |  | Draft knowledge transfer report | 8/30/22 |  |
|  |  | Final knowledge transfer report | 10/31/22 |  |